## Slide 1
US Commercial PAS Program – Weekly Status Report
Unified Status Report across Enhance, Extend, Signature Property & AMS Streams
Track: Executive Summary
AXA XL Commercial PAS Program | Deloitte Delivery Team | Internal Circulation Only Slide 1 of 5
Project Description & Governance Overview |  |  | 
Project Description: AXA XL's Commercial Policy Administration System (PAS) program drives growth across US Middle Market and Wholesale sectors, supporting the entire policy lifecycle (Submission through Policy Servicing) for Commercial lines. The unified program encompasses four core delivery streams: Enhance (Middle Market platform releases R4.7 & R4.8, operational efficiency, and business priority enhancements), Extend (Wholesale PAS delivery for Primary & Excess Casualty and Energy products), Signature Property (expansion of commercial property capabilities), and AMS (Application Management Services & ongoing production support). |  |  | 
Executive Sponsors: | Matthieu Caillat & Matthew Waters (MM) ¦ Bennett Turner (Wholesale) | Impacted Region: | United States (US)
Project Manager / Lead: | Kishore Banala (PM) ¦ Delivery Lead: Gaurav | CDF Phase & Compliance: | CDF Phase: Deliver ¦ Stage Gate Compliance: 🟢 Compliant
Delivery Stream | Enhance | Extend (Wholesale) | Signature Property | AMS
Current RAG Status | 🟢 GREEN | 🟢 GREEN | 🟢 GREEN | 🟢 GREEN
Key Delivery Highlights | R4.7 Pre-Prod & R4.8 Sprint testing on track | Wholesale Pilot and Excess Casualty on schedule | Track mobilization and rating ROCs on schedule | Application support baseline and stabilization on track
Delivery Stream | Milestone / Release Name | Baseline Finish (MM/DD/YY) | Schld / Actual Finish | Status | Executive Comments
Enhance |  |  |  |  | 
Extend (Wholesale) |  |  |  |  | 
Signature Property |  |  |  |  | 
AMS |  |  |  |  | 
Program Release Gate |  |  |  |  | 

## Slide 2
Extend / Wholesale – Project Status Report
Functional Progress across Integration, Configuration, Rating & Forms | Leads: Mousumi, Arshad, Juhitha
Stream: Extend (Wholesale)
AXA XL Commercial PAS Program | Deloitte Delivery Team | Internal Circulation Only Slide 2 of 5
Product Factory – Key Highlights ¦ Lead: Mousumi
• Inland Marine: Built Product Model design for Contractor's Equipment & Builder's Risk; preparing Motor Truck Cargo workshop. • Forms Audit: Executing iterations on data extraction approach with additional tokens; prepping Check #2 comparison. • MM Excess Casualty & Signature Property: Functional mobilization support completed; queries addressed across dev & QA teams.
Product Factory – Focus for Next 2 Weeks
• Inland Marine: Finalize Product Model design across coverage parts; conduct business alignment sessions. • Forms Audit: Initiate Check #2 analysis (Guidewire comparison) post verification of data extraction accuracy. • MM Excess Casualty & Signature Property: Continue ongoing mobilization support and validation with dev & QA factories.
Key Highlights | Requirement | Development | QA
Integration | Finalized dynamic endorsement form data mapping & Xpath requirements (154 dynamic forms scoped). | Completed Dynamic Part 6 endorsements (51 forms) & dynamic Declarations; EPDS & SmartCOMM sync ongoing. | Completed QA on 90% of Oct 2 release items; regression testing on SmartCOMM endorsement parts 2, 3, 5 complete.
Configuration | Completed specs for Policy Number Generation, Auto Granularity-1, Policy Review & Payments; Cancellation in progress. | Completed Modifiers, Product Model-1, Forms Support-2, and Rating Support-1; Line Level & Pricing screens in dev. | Executing test cases on Product Model clauses and Underlying Limits (UL) schedule screens.
Rating | Supported rating workshops and gathered rating requirements for new Auto granularity rating on MM Excess Casualty. | Developed Auto XS Layer, Terrorism Premium, Commission/Acquisition, and SIR capabilities; final premium algos in dev. | Completed validation of Support Card & GL class code rate tables; testing terrorism premium and auto exp mod calculations.
Forms | Finalized 300+ form requirements across Primary/Excess Casualty and Energy; dynamic endorsement specs under review. | Completed form # and name validations, display form number with clause names Part II across Casualty & Energy. | Resolved UAT observations for August & September releases; completed 90% of Oct 2 release form verifications.
Next 2 Weeks | Requirement | Development | QA
Integration | Complete requirement gathering for WINS and Netreveal integration points. | Deliver development implementation of WINS integration and finalize SmartCOMM Part 7 endorsement builds. | Verify UAT feedback for contract data sync and wholesale salesflow reporting; close pending Pilot issues.
Configuration | Finalize Sprint-13 planned requirement cards (Cancellation/Reinstatement, Quick Quote, Autogranularity Part 2). | Continue build for Community Model, Product Model Rules Part 2, and Line Level Pricing screens. | Complete remaining Oct 2 validation items and initiate testing on Oct 30 release test cases.
Rating | Review all rating materials and artifacts to support Define rating sessions for Inland Marine & Excess Casualty. | Deliver Sprint-15 planned items: Final Selected Premium adjustments, Crisis Management, and Min/Max cards. | Test rating routines for post-bind transactions, unsupported flow, and Quota Share calculations.
Forms | Initiate Check #2 analysis for Forms Audit and finalize requirements for October release items. | Complete remaining dynamic endorsement Xpaths and address upcoming UAT issue fixes for Casualty & Energy. | Execute end-to-end testing for Oct 16 SmartCOMM release items and pilot issue closures.
Key Risk / Watchout Item | Description & Functional Impact | Impact Category | Status | Action Mitigation Plan
Final Selected Premium Calculation (Reference) | Complex rate routine calculation logic for excess layers finalized and validated. | Technical Risk | 🟢 GREEN | Architectural review completed with Guidewire team; rate routine logic finalized.

## Slide 3
Enhance – Project Status Report
Functional Progress across Integration, Configuration, Rating & Forms | Lead: Shamanth
Stream: Enhance
AXA XL Commercial PAS Program | Deloitte Delivery Team | Internal Circulation Only Slide 3 of 5
Key Highlights | Requirement | Development | QA
Integration | Completed requirements for WINS Integration, Systemic Risk elements, and Salesflow submission statuses. | Completed EPDS contract data sync, Harta integration, wholesale salesflow reports, and WC/CA exposure reports. | Completed dev and QA for Data Studio enhancements, mock dashboards, and WC accumulation; pending UAT signoff.
Configuration | Completed requirements for WC AXICA (4.9), Enable Final Audit (CA), and Producer Name/Code updates. | Completed Premium Allocation policy change and MM Environmental Clauses; RRL phase config changes in progress. | Verified Producer Code updates and Environmental clause enablement across MM products.
Rating | Completed WC AXICA Phase 9 Rating, Manual Premium (not subject to mods), and TLR updates across all LOBs. | Raised Guidewire incident for Non-STD term proration (SBT fix) and holding regular syncs with GW team. | Verified manual premium calculation rules and rate table updates in current sprint test environment.
Forms | Completed analysis for Endorsement numbering logic (4.9) and international location forms. | Expired CUU legacy forms (4.7); deferred composite rates on QP/BP and ENV clauses to 4.9. | Documents and forms audit Part 2 under business review; QA testing on retired form versions completed.
Next 2 Weeks | Requirement | Development | QA
Integration | Complete requirement gathering on WINS and Netreveal integrations. | Implement development of WINS integration and complete Harta UAT feedback updates. | Complete UAT signoff on EPDS contract data sync and wholesale salesflow reporting.
Configuration | Finalize requirements for International Property Locations and CP Premium Allocation (4.10). | Enable Final Audit capabilities for WC based on UAT feedback; enable Property International locations. | Validate WC Final Audit workflow in sprint regression testing.
Rating | Reconcile Guidewire SBT fix directions for non-standard term proration. | Plan to close all in-progress rating calculation items and SBT incident workarounds. | Execute rating regression test pack across active MM commercial policies.
Forms | Finalize renewal term number update specifications and Forms Audit scope. | Implement CP international location forms and update renewal term numbering logic. | Complete Forms Audit verification and support regression testing for upcoming releases.
Key Risk / Watchout Item | Description & Functional Impact | Impact Category | Status | Action Mitigation Plan
Non-Standard Term Proration - SBT Fix (Reference) | Guidewire proration workaround implemented and aligned with SBT fix guidelines. | Technical Issue | 🟢 GREEN | Guidewire workaround in place; SBT directions confirmed and validated in sprint test cycle.

## Slide 4
Signature Property – Project Status Report
Commercial Property Capability Track | Delivery Lead: Shanu Jyothi
Stream: Signature Property
AXA XL Commercial PAS Program | Deloitte Delivery Team | Internal Circulation Only Slide 4 of 5
Key Highlights | Requirement | Development | QA
Integration |  |  | 
Configuration |  |  | 
Rating |  |  | 
Forms |  |  | 
Next 2 Weeks | Requirement | Development | QA
Integration |  |  | 
Configuration |  |  | 
Rating |  |  | 
Forms |  |  | 
Key Risk / Watchout Item | Description & Functional Impact | Impact Category | Status | Action Mitigation Plan

## Slide 5
AMS – Project Status Report
Application Management Services & Production Support | Delivery Lead: Swetlana
Stream: AMS
AXA XL Commercial PAS Program | Deloitte Delivery Team | Internal Circulation Only Slide 5 of 5
Key Highlights | Requirement | Development | QA
Integration |  |  | 
Configuration |  |  | 
Rating |  |  | 
Forms |  |  | 
Next 2 Weeks | Requirement | Development | QA
Integration |  |  | 
Configuration |  |  | 
Rating |  |  | 
Forms |  |  | 
Key Risk / Watchout Item | Description & Functional Impact | Impact Category | Status | Action Mitigation Plan